## W1-W5 Task Plan
Epic | Feature | Task | Layer | Owner | Week | Milestone | Status | Remarks
Foundations & Auth | Dev Environment Setup | Inspect existing frontend prototype and repository setup; note what is reused vs rebuilt | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 1/7 (timebox ½ day). Existing frontend/ prototype is exploratory. Done when: short note lists reused vs rebuilt items and is shared with the team.
Foundations & Auth | Dev Environment Setup | Set up monorepo and React 19 + Vite frontend scaffold with linting and folder conventions | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 2/7. Approved stack: React frontend, Python/FastAPI backend. Done when: app builds and runs locally, lint passes, README has run steps.
Foundations & Auth | UI Framework & Base Layout | Create design tokens and shared UI components (button, card, select, badge, modal, spinner) | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 3/7 — build only the components needed for login and dashboard first. Based on current UI mockups; final Figma approval not yet confirmed. Done when: components render default, disabled and loading states and are used by the login screen.
Foundations & Auth | UI Framework & Base Layout | Build application shell: header, page layout and routes (Login, Dashboard, Workspace) | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 4/7. Based on current UI mockups; final Figma approval not yet confirmed. Done when: Login, Dashboard and Workspace routes render inside the shared layout; unknown route shows a not-found page.
Foundations & Auth | Login Page UI | Build login screen UI (welcome card, SSO badge, email field, Sign-in button) | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 5/7. Based on current UI mockups; final Figma approval not yet confirmed. Done when: screen matches login mockup, email format validation works, form usable by keyboard (Tab/Enter).
Foundations & Auth | Login Page UI | Mock sign-in and route guard | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 6/7. Mock authentication only — real Entra ID SSO is not part of M1 or M2. Done when: unauthenticated user is redirected to login, mock session survives refresh, screen shows a "mock sign-in" label.
Main Page & Parameters | KBI Header Bar & Tabs UI | Start dashboard page structure (KPI row, filter area, recent reports area) — deferrable to early W2 if W1 overruns | FE | Vishwachandra | W1 (12–16 Oct) | M1 | Not Started | W1 order 7/7 — DEFERRABLE: may move to Mon–Tue of W2 if W1 overruns; M1 date (23 Oct) unchanged. Done when: empty dashboard layout with KPI, filter and recent-report areas renders after mock sign-in.
Foundations & Auth | API Contracts & Mock Services | Inspect existing backend setup and agree API conventions (FastAPI, Pydantic models, error format) | BE | Sudhakshina | W1 (12–16 Oct) | M1 | Not Started | No backend service exists in the workspace yet. Done when: naming, error format and versioning conventions are agreed with frontend and written in README.
Foundations & Auth | API Contracts & Mock Services | Set up FastAPI mock service skeleton per approved stack | BE | Sudhakshina | W1 (12–16 Oct) | M1 | Not Started | Serves mock data for frontend demos. Done when: service starts locally, health endpoint returns OK, lint passes.
Foundations & Auth | API Contracts & Mock Services | Define initial API contracts: session, KPI cards, filter options, recent reports | BE | Sudhakshina | W1 (12–16 Oct) | M1 | Not Started | Review with Vishwachandra before W2. Done when: OpenAPI draft covers session, KPIs, filters and recent reports and is agreed by frontend.
Foundations & Auth | API Contracts & Mock Services | Implement mock responses for login and dashboard endpoints | BE | Sudhakshina | W1 (12–16 Oct) | M1 | Not Started | Fictional data, clearly labelled as mock. Done when: every M1 endpoint returns contract-conformant mock data, checked by simple API tests.
Main Page & Parameters | KBI Header Bar & Tabs UI | KPI cards (RSV, Market Share, Volume, Weighted Distribution, HH Penetration) with CMI / Finance / Brand Category tabs | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | Mock data only. Done when: five cards show value and change from the mock service, tab switch changes the card set, values are labelled mock.
Main Page & Parameters | Parameter Selection Form UI | Region, Market (dependent on Region) and Presentation Template filters with validation | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | Mock data only. Pulled forward from W3–W4 in the original plan. Done when: Market list updates on Region change, invalid combinations show a message, Generate Narrative stays disabled until all three are valid.
Main Page & Parameters | Recent FNOS Reports UI | Recent Reports cards with Draft / Published status badges | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | Mock data only. Pulled forward from W3–W4 in the original plan. Done when: cards render from the mock service with correct status badges; empty state shows when the list is empty.
Foundations & Auth | UI Framework & Base Layout | Connect dashboard components to mock services through a shared API client | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | Mock data only. Done when: no hard-coded data in components; mock service URL configurable without code change.
Foundations & Auth | UI Framework & Base Layout | Loading, empty and error states for dashboard data | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | Uses mock slow/error responses. Done when: loading skeleton, error message with Retry, and empty message each verified using the mock toggles.
Foundations & Auth | UI Framework & Base Layout | Verify login → dashboard flow and prepare M1 demo | FE | Vishwachandra | W2 (19–23 Oct) | M1 | Not Started | M1 demo: 23 Oct. Done when: scripted walkthrough (login → dashboard → KPI tabs → filters → recent reports) passes twice on the demo machine in Edge and Chrome; known gaps listed.
Foundations & Auth | API Contracts & Mock Services | Complete dashboard mock endpoints, including slow and error simulation | BE | Sudhakshina | W2 (19–23 Oct) | M1 | Not Started | Mock data only. Done when: slow and error modes can be toggled for each dashboard endpoint.
Foundations & Auth | API Contracts & Mock Services | Publish OpenAPI contract and mock-service run instructions; review with frontend | BE | Sudhakshina | W2 (19–23 Oct) | M1 | Not Started | Done when: contract is versioned in the repo and frontend confirms it matches what the UI uses.
Foundations & Auth | API Contracts & Mock Services | Verify mock API responses against the contract for the M1 demo | BE | Sudhakshina | W2 (19–23 Oct) | M1 | Not Started | Done when: contract check passes for all M1 endpoints before the demo.
Foundations & Auth | Federated SSO & Auth API | Design Entra ID JWT validation middleware | BE | Sudhakshina | W2 (19–23 Oct) | — | Not Started | Design only — not part of M1 or M2. Live integration depends on Entra ID app registration, APIM configuration and security configuration (Mars IAM/platform). Done when: design note covering token validation, claims and the APIM role is reviewed by the team.
Main Page & Parameters | Parameter Selection Form UI | Generate Narrative action with simulated response (enabled only when filters are valid) | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Simulated; no AI or Databricks. Done when: button disabled until filters valid; click shows a progress state and opens the workspace with a simulated report ID.
Presentation Canvas & Slides | Slide Thumbnail Navigation | Navigation from dashboard to report workspace (report context, Back to dashboard) | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Done when: workspace URL includes the report ID, refresh reloads the same mock report, Back returns to the dashboard with filters kept.
Presentation Canvas & Slides | 16:9 Slide Canvas Viewer | PowerPoint-style three-pane workspace layout (left rail, centre canvas, right panel) | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Based on current UI mockups; final Figma approval not yet confirmed. Done when: three panes match mockup proportions at 1366 px and 1920 px widths.
Presentation Canvas & Slides | Slide Thumbnail Navigation | Left slide thumbnail rail using representative mock slides | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Representative mock slides, not the master template. Done when: rail lists all mock slides, scrolls smoothly, thumbnails labelled mock.
Presentation Canvas & Slides | 16:9 Slide Canvas Viewer | Centre 16:9 slide canvas (fixed aspect ratio, scales to container) | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Original story scheduled W4 only. Done when: slide keeps an exact 16:9 ratio at all supported widths with no distortion.
Presentation Canvas & Slides | Slide Thumbnail Navigation | Slide selection state and navigation (click, next / previous) | FE | Vishwachandra | W3 (26–30 Oct) | M2 | Not Started | Done when: clicking a thumbnail or using next/previous updates the highlight and the canvas consistently.
Foundations & Auth | API Contracts & Mock Services | Mock Generate Narrative endpoint returning a simulated report ID and status | BE | Sudhakshina | W3 (26–30 Oct) | M2 | Not Started | Simulated response only. Done when: endpoint returns a report ID and status after a short simulated delay; a failure mode is available.
Foundations & Auth | API Contracts & Mock Services | Mock slide list and slide detail endpoints with a representative slide set | BE | Sudhakshina | W3 (26–30 Oct) | M2 | Not Started | Not all 80 slides. Dependency: editable ~80-slide master template not in workspace; does not block mock UI. Done when: list and detail endpoints return a representative slide set labelled mock.
Foundations & Auth | Federated SSO & Auth API | Implement JWT validation middleware with test tokens and unit tests | BE | Sudhakshina | W3 (26–30 Oct) | — | Not Started | Unit-tested with locally generated test tokens only; not part of M1 or M2 (demos use mock sign-in). Live integration depends on Entra ID app registration, APIM configuration and security configuration (Mars IAM/platform). Done when: valid test token accepted; expired, wrong-audience and tampered tokens rejected; tests pass.
Presentation Canvas & Slides | Slide Thumbnail Navigation | Complete slide selection and preview behaviour (active highlight, slide counter, keyboard) | FE | Vishwachandra | W4 (2–6 Nov) | M2 | Not Started | Done when: active slide highlighted, counter shows "n of N", keyboard next/previous works. Keyboard support is the first item to cut if W4 is tight.
AI Co-Pilot & Commentary | Right Side AI & Commentary Panel | Editable commentary field for the selected slide (pre-filled with mock commentary) | FE | Vishwachandra | W4 (2–6 Nov) | M2 | Not Started | Pulled forward from W7–W8 in the original plan. Simulated only: edits held in memory for the session — no database, no PPTX change. Done when: field shows the selected slide's mock commentary, is editable, and shows a character count.
AI Co-Pilot & Commentary | Right Side AI & Commentary Panel | Ask AI panel UI with clearly labelled simulated responses | FE | Vishwachandra | W4 (2–6 Nov) | M2 | Not Started | No real AI. Pulled forward from W7–W8 in the original plan. Done when: prompt and suggested-prompt chips return canned responses, each labelled "Simulated response".
Foundations & Auth | API Contracts & Mock Services | Mock commentary get/save (in-memory, session only) and simulated Ask AI response endpoints | BE | Sudhakshina | W4 (2–6 Nov) | M2 | Not Started | Simulated responses, clearly labelled; in-memory only — no database. Done when: commentary get/save and Ask AI endpoints return contract-conformant responses, and saved text is returned on the next get within the same session.
Distribution & PPTX Engine | PowerPoint Template Setup | Prepare template inspection checklist and draft slide manifest structure | BE | Sudhakshina | W4 (2–6 Nov) | — | Not Started | Dependency: editable ~80-slide master template not in workspace; does not block mock UI. Template decomposition starts once the template is received. Done when: checklist and draft manifest structure are reviewed with the team.
AI Co-Pilot & Commentary | Right Side AI & Commentary Panel | Connect selected-slide state to commentary and Ask AI panels; simulated Save to Slide with confirmation | FE | Vishwachandra | W5 (9–13 Nov) | M2 | Not Started | Save to Slide is simulated (in-memory mock endpoint, session only). Done when: switching slides shows that slide's commentary; Save shows a confirmation; edited text reappears when returning to the slide in the same session. Fallback if W5 is tight: editable field with confirmation-only Save. Moved from W4 to W5 (M2 extended to 13 Nov).
Presentation Canvas & Slides | 16:9 Slide Canvas Viewer | Responsive behaviour and loading / empty states for the workspace | FE | Vishwachandra | W5 (9–13 Nov) | M2 | Not Started | Scope limited to laptop (1366×768) and desktop (1920×1080) widths. Done when: panels usable at both sizes; loading and empty states shown for slide list and side panels. Moved from W4 to W5 (M2 extended to 13 Nov).
Presentation Canvas & Slides | 16:9 Slide Canvas Viewer | Test full mock flow (login → dashboard → Generate Narrative → workspace) and prepare M2 demo | FE | Vishwachandra | W5 (9–13 Nov) | M2 | Not Started | M2 demo: 13 Nov. Done when: scripted walkthrough (login → dashboard → Generate Narrative → select slides → edit commentary → Save to Slide → Ask AI) passes twice on the demo machine; all mock/simulated elements labelled; known gaps listed. Includes fixing defects found during testing. Moved from W4 to W5 (M2 extended to 13 Nov).
Foundations & Auth | API Contracts & Mock Services | Verify workspace mock APIs and support M2 demo rehearsal | BE | Sudhakshina | W5 (9–13 Nov) | M2 | Not Started | Done when: contract checks pass for workspace endpoints and the mock service stays stable through two demo rehearsals. Moved from W4 to W5 (M2 extended to 13 Nov).

## Milestones
Milestone | Target Date | Demo Deliverable | Acceptance Criteria | Status | Remarks
M1 | 2026-10-23 | Login and Dashboard UI using mock data | Login screen with mock sign-in; dashboard with KPI cards and CMI / Finance / Brand Category tabs; Region, Market and Template filters with validation; Recent Reports cards with status; loading, empty and error states; all data served by mock services and labelled as mock. Scripted walkthrough passes on the demo machine. Real Entra ID SSO is not included. | Not Started | Entra ID not integrated (live sign-in depends on app registration, APIM and security configuration). Dashboard skeleton may slip into early W2 without moving this date. Based on current UI mockups; final Figma design approval not yet confirmed.
M2 | 2026-11-13 | PowerPoint-style report workspace using mock data | Generate Narrative returns a simulated result and opens the workspace; three-pane layout; left thumbnail rail with representative mock slides; selected slide shown in 16:9 canvas; editable commentary field for the selected slide with a simulated Save to Slide (confirmation shown, edited text reappears when returning to the slide in the same session); Ask AI panel with simulated responses follows the selected slide; basic responsive (laptop/desktop), loading and empty states; scripted walkthrough passes on the demo machine. | Not Started | Not required for M2: all 80 actual slides, real AI, real Databricks data, real SSO, database persistence of commentary, PPTX generation or modification. Save to Slide is simulated (in-memory, session only). Fallback if W5 slips: editable field with confirmation-only Save. Dependency: editable ~80-slide master template not in workspace; does not block mock UI. Date moved from 6 Nov (W4) to 13 Nov (W5) by agreement.