## Webapp Plan
Epic | Feature | User Story | Layer | Owner | W1 | W2 - M1 | W3 | W4 | W5 - M2 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Notes
Foundations & Auth | Dev Environment Setup | Set up the monorepo and React frontend, and review the existing prototype for reuse | FE | Vishwachandra | [14 empty] | W1–W5 plan: 2 tasks. Backend service set-up is covered under API Contracts & Mock Services.
Foundations & Auth | UI Framework & Base Layout | Set up common styles, reusable UI components and the app shell | FE | Vishwachandra | [14 empty] | W1–W5 plan: 2 tasks. Final Figma designs are pending.
Foundations & Auth | Login Screen | Login screen with mock sign-in | FE | Vishwachandra | [14 empty] | W1–W5 plan: 2 tasks. Real Entra ID sign-in comes later. Final Figma designs are pending.
Foundations & Auth | API Contracts & Mock Services | Define API contracts and build the mock API used by the Dashboard and PowerPoint Workspace demos | BE | Sudhakshina | [14 empty] | W1–W5 plan: 11 tasks. Includes the FastAPI mock service set-up.
Foundations & Auth | Federated SSO & Auth API | Entra ID token validation and API security controls | BE | Sudhakshina | [14 empty] | W1–W5 plan: 2 tasks. Design and test-token work only in W2–W3. Not part of M1 or M2. Live sign-in needs Entra ID app registration, APIM and security setup. Security controls (CORS, headers) not yet scheduled.
Dashboard & Parameters | Dashboard Layout & KPI Cards | Dashboard layout and KPI cards with CMI, Finance and Brand Category tabs, including loading, empty and error states | FE | Vishwachandra | [14 empty] | W1–W5 plan: 5 tasks. Delivered in M1 with mock data. Final Figma designs are pending.
Dashboard & Parameters | Report Filters & Generate Narrative | Region, Market and Template filters, and the Generate Narrative action | FE | Vishwachandra | [14 empty] | W1–W5 plan: 2 tasks. Filters are in M1. Generate Narrative (simulated) is in M2.
Dashboard & Parameters | Recent Reports | Recent Reports cards with Draft and Published status | FE | Vishwachandra | [14 empty] | W1–W5 plan: 1 task. Delivered in M1 with mock data.
Presentation Canvas & Slides | Slide Thumbnail Navigation | Slide thumbnail panel with slide selection and navigation | FE | Vishwachandra | [14 empty] | W1–W5 plan: 3 tasks. Uses sample slides, not the real template. Delivered in M2.
Presentation Canvas & Slides | PowerPoint Workspace Layout & Slide Preview | PowerPoint Workspace layout, navigation from the Dashboard and 16:9 slide preview, plus responsive layout and end-to-end demo testing | FE | Vishwachandra | [14 empty] | W1–W5 plan: 5 tasks. Delivered in M2. Final Figma designs are pending. W4 is shown as active to reflect continuous Workspace work. Task-level weeks are unchanged.
Distribution & PPTX Engine | PowerPoint Template Setup | Prepare the template review and slide manifest, then break the master deck into reusable slide layouts once the editable template is received | BE | Sudhakshina | [14 empty] | W1–W5 plan: 1 task. W4 covers preparation only. Waiting for the editable ~80-slide PowerPoint template.
Dashboard & Parameters | Database Connection & ORM | Azure SQL DB Connection and SQLAlchemy ORM Layer (Consuming DS-managed schema and application tables) | BE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Dashboard & Parameters | Parameter & Report APIs | REST Endpoints for KBI metrics, filter options and recent report history (Consuming live DS tables) | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5. Will replace the mock Dashboard API.
Presentation Canvas & Slides | Analytics Data Integration | Connect Backend to Databricks to Fetch Brand Performance Metrics | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5. Needs the Databricks data contract and access.
AI Co-Pilot & Commentary | Slide Commentary Editor | Connect Commentary editing and Save to Slide to the persistence API | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5. The Commentary editor UI and simulated Save to Slide are delivered in M2 under Commentary & Ask AI Panel.
Presentation Canvas & Slides | Data Caching & Performance | Implement Data Caching for Fast Slide Loading and Navigation | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
Presentation Canvas & Slides | Presentation Orchestrator Engine | Setup Background Job Processing to Manage Long-Running Deck Generation | BE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Presentation Canvas & Slides | Real-Time Progress Streaming | Report Generation Job Progress Tracking via Server-Sent Events (SSE) | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5. M2 shows simulated progress only.
AI Co-Pilot & Commentary | Commentary & Ask AI Panel | Right panel with editable Commentary, simulated Save to Slide and Ask AI with simulated responses | FE | Vishwachandra | [14 empty] | W1–W5 plan: 3 tasks. Real AI and database saving come later.
Presentation Canvas & Slides | Deck Slide Synchronization | Deck Navigation: Active Slide Switching and Data Synchronization across 80 Slides | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5. Slide switching with sample slides is delivered in M2.
AI Co-Pilot & Commentary | Slide Edit Persistence API | Slide Narrative Delta Persistence API (Storing user edits in DS-provided Azure SQL tables) | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
Distribution & PPTX Engine | Distribution Modal Dialog UI | Distribute Report Modal Dialog: Title input, recipient group pills (Executive Board/Managers) and Summary | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
GenAI Synthesis & Copilot | Azure OpenAI Integration | Setup Secure Azure OpenAI Service to Generate Structured Slide Commentary | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
GenAI Synthesis & Copilot | Slide Narrative Generation | Build AI Commentary Generation API with Business Rules and Guardrails | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
Distribution & PPTX Engine | Executive Summary & Regeneration | Generate AI Executive Summary with Live Regeneration Action in Distribution Modal | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Distribution & PPTX Engine | Enterprise Email Service | Enterprise Email Integration (Microsoft Graph API / SendGrid): Dispatch Report to Selected Groups | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
Distribution & PPTX Engine | Automated PowerPoint Generator | Build Serverless Worker to Populate and Generate Full 80-Slide PowerPoint Deck (Azure function) | BE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5. Needs the editable PowerPoint template.
GenAI Synthesis & Copilot | Interactive AI Assistant | Implement Conversational Q&A Assistant Streaming Backend Endpoint in Right Panel | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
GenAI Synthesis & Copilot | Slide Chart Components | Build Interactive Chart Visualizations for Brand Share and Trend Slides | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Distribution & PPTX Engine | Secure Report Download | Generate Secure Temporary Download Links to Export PowerPoint Files from Azure Storage | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
GenAI Synthesis & Copilot | Accessibility & Polish | Accessibility, Cross-Browser Compatibility and UI Polish | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Hardening & Code Freeze | Frontend State Optimization | Frontend Rendering Optimization, Memory Leak Prevention, Error Boundaries and Toast System | FE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5.
Hardening & Code Freeze | Backend Query Profiling & Tuning | Analytical Query Profiling, In-Memory Caching Rules, Connection Pooling and Async Thread Tuning | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
Hardening & Code Freeze | 80-Slide Rendering Latency Tuning | 80-Slide PowerPoint Generation Optimization (Sub-second target) and Memory Profiling | BE | Vishwachandra | [14 empty] | Backlog. Schedule to be agreed after W5. Performance target to be agreed.
Hardening & Code Freeze | Final Feature Freeze & Release Build | Final Production Backend Packaging, Container Build and Handoff to Testing Team | BE | Sudhakshina | [14 empty] | Backlog. Schedule to be agreed after W5.
GenAI Synthesis & Copilot | Multi-Agent AI Integration | Integrate with the approved multi-agent AI architecture (Router, Manager, SQL, Python, Insights and Summarizer agents) | BE | TBD | [14 empty] | Backlog. Owner and schedule to be agreed after W5.

## Milestones
Milestone | Week | Target Date | Deliverable | Acceptance Criteria | Status
M1 | W2 | 2026-10-23 | Login and Dashboard with mock data | Login screen with mock sign-in. Dashboard with KPI cards and CMI, Finance and Brand Category tabs. Region, Market and Template filters with validation. Recent Reports with status. Loading, empty and error states. All data comes from the mock service and is labelled as mock. The demo walkthrough runs cleanly on the demo machine. | Not Started
M2 | W5 | 2026-11-13 | PowerPoint Workspace with mock data | Generate Narrative opens the PowerPoint Workspace with a simulated report. Three-panel layout with sample slide thumbnails and a 16:9 slide preview. Editable Commentary for each slide with a simulated Save to Slide. A confirmation is shown, and edits remain when returning to the slide in the same session. Ask AI panel with simulated responses that follow the selected slide. Works on laptop and desktop screens, with loading and empty states. The demo walkthrough runs cleanly on the demo machine. | Not Started