## DS Team Plan
Epic | Feature | User Story | Owner | W1 | W2 | W3 | W4 - M1 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
Data Foundation and Ingestion | KPI Logic Mapping | Finance - Financial Performance KPI Logic | Ravirajbhai
Data Foundation and Ingestion | KPI Logic Mapping | CMI - Drive Relevance KPI Logic | Jesu
Data Foundation and Ingestion | KPI Logic Mapping | Finance - Drive Relevance and EU Overview KPI Logic | Ravirajbhai
Data Foundation and Ingestion | Data Transformation and Processing | Finance + CMI - Data Pipelines Build | Ravirajbhai / Jesu
Data Foundation and Ingestion | Data Transformation and Processing | Finance + CMI - Data Pipelines Build | Ravirajbhai / Jesu
Data Foundation and Ingestion | Review and Validation | KPI Validation | Ravirajbhai / Jesu
Data Foundation and Ingestion | Review and Validation | ETL Pipeline Testing and Validation | Ravirajbhai / Jesu
PPT Automation | Master Template Decomposition | Deconstruction of Master Template | Kavya
PPT Automation | Master Template Decomposition | Creation of Reusable Assets from Decomposed PPT Slides | Kavya
PPT Automation | Deterministic Logic Mapping | Build python scripts to generate slides and populate from Processed data | Kavya | bar: W5 to W6
GenAI Insight Synthesis | Automated Insight Generation - Pre-Processed Analytical Layer | Knowledge Base Creation | Jesu
GenAI Insight Synthesis | Automated Insight Generation - Pre-Processed Analytical Layer | Knowledge Base Integration | Jesu/Ravirajbhai | bar: W5
GenAI Insight Synthesis | Prompt Engineering | Prompt Tuning and Guardrail Management | Jesu | bar: W5 to W9
GenAI Insight Synthesis | Prompt Engineering | Review and Validation | Kavya/Jesu | bar: W9 to W11
Webscraping | Product Reviews | Build Python Scripts for Webscraping | Raviraj/Kavya | bar: W5
Webscraping | Product Reviews | Summarize from Scraped Output into Insights | Raviraj/Kavya | bar: W5 to W7

## Webapp Plan
Epic | Feature | User Story | Layer | Owner | W1 | W2 | W3 | W4 - M1 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Foundations & Auth | Dev Environment Setup | Monorepo and App Scaffolding: React 19 + Vite Frontend, FastAPI Backend, Pydantic and Linters | BE | Vishwachandra
Foundations & Auth | UI Framework & Base Layout | Setup Base Application Styling, Common UI Components and Page Layout | FE | Vishwachandra
Foundations & Auth | Login Page UI | Login Page UI: Welcome card, Mars-Federated-SSO badge, email input (effem.com) and Sign-In button | FE | Vishwachandra
Foundations & Auth | API Contracts & Mock Services | Define API Data Models and Setup Mock APIs for Frontend Development | BE | Sudhakshina
Foundations & Auth | Federated SSO & Auth API | Azure AD / Entra ID JWT Validation Middleware and Security Controls | BE | Sudhakshina
Main Page & Parameters | KBI Header Bar & Tabs UI | Main Page KBI Header Bar (RSV, Share, Volume, Pen.) with CMI / Finance / Brand Category Tabs | FE | Vishwachandra
Main Page & Parameters | Parameter Selection Form UI | Parameter Selection Form: Region, Market, Presentation Template dropdowns and client validation | FE | Vishwachandra
Main Page & Parameters | Recent FNOS Reports UI | Recent FNOS Reports List Cards (FNOS_26_Q1/Q2/Q3, View: Total Europe Cluster, Status Badges) | FE | Vishwachandra
Presentation Canvas & Slides | Slide Thumbnail Navigation | Left Sidebar Slide Thumbnail Navigation: Mini slide preview list and active slide selection | FE | Vishwachandra
Presentation Canvas & Slides | 16:9 Slide Canvas Viewer | Main Slide Canvas: 16:9 Slide Viewer and Interactive Data Display | FE | Vishwachandra
Distribution & PPTX Engine | PowerPoint Template Setup | PowerPoint Template Engine: Deconstruct Master Deck into Reusable Slide Layouts | BE | Sudhakshina
Main Page & Parameters | Database Connection & ORM | Azure SQL DB Connection and SQLAlchemy ORM Layer (Consuming DS-managed schema and application tables) | BE | Vishwachandra | bar: W5 to W6
Main Page & Parameters | Parameter & Report APIs | REST Endpoints for KBI metrics, filter options and recent report history (Consuming live DS tables) | BE | Sudhakshina | bar: W5 to W6
Presentation Canvas & Slides | Analytics Data Integration | Connect Backend to Databricks to Fetch Brand Performance Metrics | BE | Sudhakshina | bar: W5 to W6
AI Co-Pilot & Commentary | Slide Commentary Editor | Slide Commentary Editor: In-Canvas Narrative Editing and Save-to-Slide UI | FE | Vishwachandra | bar: W6 to W7
Presentation Canvas & Slides | Data Caching & Performance | Implement Data Caching for Fast Slide Loading and Navigation | BE | Sudhakshina | bar: W6 to W7
Presentation Canvas & Slides | Presentation Orchestrator Engine | Setup Background Job Processing to Manage Long-Running Deck Generation | BE | Vishwachandra | bar: W6 to W7
Presentation Canvas & Slides | Real-Time Progress Streaming | Report Generation Job Progress Tracking via Server-Sent Events (SSE) | FE | Vishwachandra | bar: W7 to W8
AI Co-Pilot & Commentary | Right Side AI & Commentary Panel | Right Side Panel: AI Insights Assistant and Slide Commentary Editor | FE | Vishwachandra | bar: W7 to W8
Presentation Canvas & Slides | Deck Slide Synchronization | Deck Navigation: Active Slide Switching and Data Synchronization across 80 Slides | FE | Vishwachandra | bar: W7 to W8
AI Co-Pilot & Commentary | Slide Edit Persistence API | Slide Narrative Delta Persistence API (Storing user edits in DS-provided Azure SQL tables) | BE | Sudhakshina | bar: W8
Distribution & PPTX Engine | Distribution Modal Dialog UI | Distribute Report Modal Dialog: Title input, recipient group pills (Executive Board/Managers) and Summary | FE | Vishwachandra | bar: W9
GenAI Synthesis & Copilot | Azure OpenAI Integration | Setup Secure Azure OpenAI Service to Generate Structured Slide Commentary | BE | Sudhakshina | bar: W9 to W10
GenAI Synthesis & Copilot | Slide Narrative Generation | Build AI Commentary Generation API with Business Rules and Guardrails | BE | Sudhakshina | bar: W9 to W10
Distribution & PPTX Engine | Executive Summary & Regeneration | Generate AI Executive Summary with Live Regeneration Action in Distribution Modal | FE | Vishwachandra | bar: W9 to W10
Distribution & PPTX Engine | Enterprise Email Service | Enterprise Email Integration (Microsoft Graph API / SendGrid): Dispatch Report to Selected Groups | BE | Sudhakshina | bar: W10 to W11
Distribution & PPTX Engine | Automated PowerPoint Generator | Build Serverless Worker to Populate and Generate Full 80-Slide PowerPoint Deck (Azure function) | BE | Vishwachandra | bar: W10 to W11
GenAI Synthesis & Copilot | Interactive AI Assistant | Implement Conversational Q&A Assistant Streaming Backend Endpoint in Right Panel | BE | Sudhakshina | bar: W10 to W11
GenAI Synthesis & Copilot | Slide Chart Components | Build Interactive Chart Visualizations for Brand Share and Trend Slides | FE | Vishwachandra | bar: W11 to W12
Distribution & PPTX Engine | Secure Report Download | Generate Secure Temporary Download Links to Export PowerPoint Files from Azure Storage | BE | Sudhakshina | bar: W11 to W12
GenAI Synthesis & Copilot | Accessibility & Polish | Accessibility, Cross-Browser Compatibility and UI Polish | FE | Vishwachandra | bar: W12
Hardening & Code Freeze | Frontend State Optimization | Frontend Rendering Optimization, Memory Leak Prevention, Error Boundaries and Toast System | FE | Vishwachandra | bar: W13
Hardening & Code Freeze | Backend Query Profiling & Tuning | Analytical Query Profiling, In-Memory Caching Rules, Connection Pooling and Async Thread Tuning | BE | Sudhakshina | bar: W13
Hardening & Code Freeze | 80-Slide Rendering Latency Tuning | 80-Slide PowerPoint Generation Optimization (Sub-second target) and Memory Profiling | BE | Vishwachandra | bar: W13 to W14
Hardening & Code Freeze | Final Feature Freeze & Release Build | Final Production Backend Packaging, Container Build and Handoff to Testing Team | BE | Sudhakshina | bar: W14